Partial Report

Project Title：

ID JEMS:

Students:

Professor:

University:

# Declaration of Responsibility

We, students from project ID. XXXXXXX, hereby declare that the provided information in this report is true, under supervision of our professor who signed below.

Professor’s signature: _____________________________________

Professor’s name:

Date:

Proposed Schedule

[Insert proposed schedule on submission form]

| 15/04 | Send proposal |
| --- | --- |
| 20/05 | Receive board |
| 20/05 | Start documentation |
| 20/05 – 20/06 | Study board capabilities |
| 20/06 – 25/06 | Adapt project to board |
| 08/06 | Technical webinar |
| 04/07 | Receive additional material |
| 04/07 – 01/08 | Prototype development for A,B and C functionalities |
| 01/08 | Start development |
| 23/08 | Technical webinar |
| 01/09 | Conclude functionality A |
| 20/09 | Submit partial report |
| 27/09 | Conclude functionality B |
| 16/10 | Conclude functionality C |
| 16/10 – 30/10 | Correct bugs |
| 20/10 | Prepare for presentation |
| 20/10 | Finalize documentation |
| 30/10 | Submit final report |
| 03/11 – 06/11 | Presentation at SBESC |

Update Schedule

[Insert updated version of the project schedule, highlighting the accomplished tasks and their status (percentage).]

| 15/04 | Send proposal | 100 % |
| --- | --- | --- |
| 20/05 | Receive board | 100 % |
| 20/05 | Start documentation | 30 % |
| 20/05 – 20/06 | Study board capabilities | 80 % |
| 20/06 – 25/06 | Adapt project to board | 100 % |
| 08/06 | Technical webinar | 100 % |
| 04/07 | Receive additional material | 50 % |
| 04/07 – 01/08 | Prototype development for A,B and C functionalities | 100 % |
| 01/08 | Start development | 100 % |
| 23/08 | Technical webinar | 100 % |
| 01/09 | Conclude functionality A | 95 % |
| 20/09 | Submit partial report | 100 % |
| 27/09 | Conclude functionality B | 40 % |
| 16/10 | Conclude functionality C | 15 % |
| 16/10 – 30/10 | Correct bugs | - |
| 20/10 | Prepare for presentation | - |
| 20/10 | Finalize documentation | - |
| 30/10 | Submit final report | - |
| 03/11 – 06/11 | Presentation at SBESC | - |

Difficulties and Workarounds

[Write down the group’s biggest technical difficulty, so far, and how it was handled.]